## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | Generated recorded calls between sales representative and customer | MUST HAVE |  | Divya | 3- Completed
1 | 1 | US-02 | Generated the transcript for .wav audio file | MUST HAVE | 1 | Divya | 3- Completed
2 | 2 | US-03 | Live speech recordings and generated transcript for live speech records | MUST HAVE | 1 | Divya | 3- Completed
2 | 2 | US-04 | speaker diarization | MUST HAVE | 2 | Divya | 3- Completed
2 | 2 | US-05 | Should be able to download the transcriped text | SHOULD HAVE | 2 | Divya | 3- Completed
3 | 3 | US-06 | Generated Sentiment ,Intent,Entity Extraction only for Customer transcript | MUST HAVE | 2 | Divya | 3- Completed
4 | 4 | US-07 | Integrated all features into one UI and added AI suggestions,objection handling , recommended questions to the sales rep based on customer latest responses | MUST HAVE | 1,2,3 | Divya | 3- Completed
Note on F1: ====== ID#AAABxQ0wBMM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Find suitable sources and decide whether to record manulally or gather AI-generate sales call audio recordings for the dataset. | 2025-10-16 | 2025-10-16 | Divya | searched for datasets | 3- Completed | 1
US-01 | T-02 | Generate transcript from Chatgpt | 2025-10-23 | 2025-10-23 | Divya | Others | 3- Completed | 2
US-01 | T-03 | convert text file to .wav audio file | 2025-10-24 | 2025-10-24 | Divya | manully recorded audio for transcript which I have generated using chatgpt | 3- Completed | 4
US-02 | T-04 | Generate Transcript for the .wav audio file | 2025-10-27 | 2025-10-29 | Divya | Coding | 3- Completed | 2
US-03 | T-05 | Transcript the live speech | 2025-10-30 | 2025-11-03 | Divya | Coding | 3- Completed | 6
US-04 | T-06 | speaker diarization for live speech audio | 2025-11-11 | 2025-11-13 | Divya | Coding | 3- Completed | 6
US-05 | T-07 | should be able to downoad the transcribed text | 2025-11-14 | 2025-11-15 | Divya | Coding | 3- Completed | 1
US-06 | T-08 | Generate Sentiment Analysis,Intent Analysis,Entity Extraction only for Customer responses | 2025-11-25 | 2025-11-27 | Divya | Coding | 3- Completed | 10
US-07 | T-09 | Create UI by integrating all previous tasks | 2025-11-28 | 2025-11-30 | Divya | Coding | 3- Completed | 7
US-08 | T-10 | Integrated all features into one UI and added AI suggestions,objection handling , recommended questions to the sales rep based on customer latest responses | 2025-11-30 | 2025-12-08 | Divya | Coding | 3- Completed | 12
Note on D2: ====== ID#AAABxQ0wBMg Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABxQ0wBL8 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABxQ0wBMY Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABxQ0wBLg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABxQ0wBLo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABxQ0wBME Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABxQ0wBL0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABxQ0wBMI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABxQ0wBLw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABxQ0wBMU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABxQ0wBMA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABxQ0wBL4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABxQ0wBLk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABxQ0wBMQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABxQ0wBMc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABxQ0wBLc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABxQ0wBLs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-10-16 | Instructions to start work on the dataset | Begin the work
2 | 2025-10-24 | Discussing the outcomes from Sprint 1 | Add 2 min audio clips for all dataset
2 | 2025-11-19 | Discussing the outcomes from Sprint 2 | Added Speaker diarization
3 | 2025-11-22 | Adding UI | Action Taken
3 | 2025-11-29 | Adding Emotion detection to customer texts | Implemented
4 | 2025-12-08 | Integrate all 3 milestones to One UI | Finished

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-16 | 2025-10-24 | Divya | Data Collection |  |  | Researched
2 | 2 | 2025-11-12 | 2025-11-19 | Divya | Live Speech | Data Collection | Speaker Diarization | Reseached &Started coding
3 | 3 | 2025-11-25 | 2025-12-05 | Divya | Intent analysis | Transcription part | Developing UI | Added a feature for customer text
4 | 4 | 2025-12-06 | 2025-12-10 | Divya | AI suggestion | Developing UI | AI analysis part | Added UI and AI integration to project