## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DEF-01 | Divya | 2025-10-23 | System fails to accurately transcribe some words from recorded calls | 1 | Divya | Logical | Improved noise filtering and adjusted speech recognition configuration to handle fast speech. | 2025-10-21 | closed | Issue occurs with fast speech
DEF-02 | Divya | 2025-10-24 | System takes excessive time to convert long recorded calls into text | 1 | Divya | Logical | Optimized audio chunk processing and reduced transcription latency | 2025-10-22 | closed | Delay observed for audio files longer than 5 minutes
DEF-03 | Divya | 2025-11-03 | Background noise affects transcription accuracy in recorded calls | 2 | Divya | Logical | Enhanced noise reduction techniques during audio preprocessing | 2025-11-01 | closed | Accuracy drops in noisy environments
DEF-04 | Divya | 2025-11-13 | System fails to perform proper speaker diarization | 2 | Divya | Logical | Upgraded PyAnnote library and aligned it with a compatible Python version | 2025-11-09 | closed | Issue occurred due to incompatibility between Python and PyAnnote versions
DEF-05 | Divya | 2025-11-20 | System fails to accurately extract entities from transcribed call data | 3 | Divya | Logical | Improved entity extraction logic and updated NLP rules to enhance accuracy ¦ | 2025-11-15 | closed | Incorrect entity detection observed for names
DEF-06 | Divya | 2025-12-05 | AI suggestions are not updated in real time based on latest customer responses | 4 | Divya | Logical | Optimized response processing pipeline and refreshed suggestion generation logic | 2025-12-01 | closed | Observed delay when switching between customer responses

## Sheet2
Logical
User Interface
Maintainability
Standards
Others